## WBS
Software Engeneering Project Work Breakdown Structure (WBS)
Done
In-progress
Delayed
Today |  | 2021-12-29
Project Team Name |  | Group 8
Project Topic |  | JabRef Analysis Project
[8 empty] | During this time period we agreed not to work on the project as we had many other evalutations and projects. | [42 empty] | Christmas Break
Task |  |  | Start date | End date | Responsibility | Task Status | W1 | [6 empty] | W2 | [6 empty] | W3 | [6 empty] | W4 | [6 empty] | W5 | [6 empty] | W6 | [6 empty] | W7 | [6 empty] | W8
[7 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30 | D31 | D32 | D33 | D34 | D35 | D36 | D37 | D38 | D39 | D40 | D41 | D42 | D43 | D44 | D45 | D46 | D47 | D48 | D49 | D50 | D51 | D52 | D53 | D54 | D55 | D56
 | time axis 2021-11-10 to 2022-01-04
1.Planning | [5 empty] | Done
1.1 | Create repository |  | 2021-11-10 | 2021-11-10 | All | Done | bar: 2021-11-10; 2021-12-31 to 2022-01-04
1.2 | Decide Scrum Masters |  | 2021-11-10 | 2021-11-10 | All | Done | bar: 2021-11-10; 2021-12-31 to 2022-01-04
1.3 | Build WBS |  | 2021-12-05 | 2021-12-05 | All | Done | bar: 2021-12-05; 2021-12-31 to 2022-01-04
1.4 | Build Burnout Chart |  | 2021-12-05 | 2021-12-05 | All | Done | bar: 2021-12-05; 2021-12-31 to 2022-01-04
1.5 | Divide tasks |  | 2021-12-05 | 2021-12-05 | All | Done | bar: 2021-12-05; 2021-12-31 to 2022-01-04
2. Tasks Phase 1
2.01 | Detect code smells. |  | 2021-11-27 | 2021-12-04 | All | Done | bar: 2021-11-27 to 2021-12-04; 2021-12-31 to 2022-01-04
2.02 | Detect design patterns. |  | 2021-11-27 | 2021-12-04 | All | Done | bar: 2021-11-27 to 2021-12-04; 2021-12-31 to 2022-01-04
2.03 | Review Design Patterns and Code Smells. |  | 2021-12-03 | 2021-12-04 | All | Done | bar: 2021-12-03 to 2021-12-04; 2021-12-31 to 2022-01-04
2.04 | Analyse code using 5 types of metrics available. |  | 2021-12-03 | 2021-12-04 | All | Done | bar: 2021-12-03 to 2021-12-04; 2021-12-31 to 2022-01-04
2.05 | Review Code Metrics Documents developed. |  | 2021-12-03 | 2021-12-04 | All | Done | bar: 2021-12-05; 2021-12-31 to 2022-01-04
2.06 | Make use case diagrams. |  | 2021-12-05 | 2021-12-05 | All | Done | bar: 2021-12-05; 2021-12-31 to 2022-01-04
2.07 | Review use case diagrams developed. |  | 2021-12-05 | 2021-12-05 | All | Done | bar: 2021-12-05; 2021-12-31 to 2022-01-04
2.08 | Develop Sprint Backlogs. |  | 2021-12-05 | 2021-12-05 | All | Done | bar: 2021-12-05; 2021-12-31 to 2022-01-04
2.09 | Develop burndown Charts. |  | 2021-12-05 | 2021-12-05 | All | Done | bar: 2021-12-05; 2021-12-31 to 2022-01-04
2.1 | Finish phase 1 with the needed merge docs. |  | 2021-12-05 | 2021-12-06 | All | Done | bar: 2021-12-05 to 2021-12-06; 2021-12-31 to 2022-01-04
2.1.1 | Review names of produced documents. |  | 2021-12-06 | 2021-12-06 | All | Done | bar: 2021-12-05 to 2021-12-06; 2021-12-31 to 2022-01-04
3. Tasks Phase 2
3.01 | Subdivide functionality 1 into subtasks. |  | 2021-12-15 | 2021-12-23 | 57672+57957+58210 | Done | bar: 2021-12-15 to 2021-12-23; 2021-12-31 to 2022-01-04
3.02 | Subdivide functionality 2 into subtasks. |  | 2021-12-15 | 2021-12-23 | 58175+57911 | Done | bar: 2021-12-15 to 2021-12-23; 2021-12-31 to 2022-01-04
3.03 | Know how to compile JabRef in each computer. |  | 2021-12-15 | 2021-12-23 | All | Done | bar: 2021-12-15 to 2021-12-23; 2021-12-31 to 2022-01-04
3.1 | Implementation phase | bar: 2021-12-31 to 2022-01-04
3.1.1 | Implement functionality 1 fully |  |  |  |  | In-progress | bar: 2021-12-26 to 2021-12-29; 2021-12-31 to 2022-01-04
3.1.2 | Implement functionality 2 fully |  |  |  |  | In-progress | bar: 2021-12-26 to 2021-12-29; 2021-12-31 to 2022-01-04