## WBS
Capstone Project Work Breakdown Structure (WBS)
Done
In-progress
Delayed
Today |  | 2021-11-19
Project Team Name |  | JefRefImprovers
Project Topic |  | JefRef
Task |  |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 |  |  | W2 |  |  |  |  | W3 |  |  |  |  | W4 |  |  |  |  | W5
[8 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19
[8 empty] | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30
1.Planning | [6 empty] | Done
| 1.1 Create repository |  | 2021-11-12 |  | All | bar: 2021-11-12 to 2021-11-13
| 1.2 Decide Scrum Masters |  | 2021-11-12 |  | All | bar: 2021-11-12 to 2021-11-13
| 1.3 Build WBS |  | 2021-09-02 | 2021-09-02 | All |  | Done | bar: 2021-11-14 to 2021-11-15
| 1.4 Build Burnout Chart |  | 2021-09-02 | 2021-09-02 | All |  | Done | bar: 2021-11-16 to 2021-11-17
1.5 Divide tasks | bar: 2021-11-18 to 2021-11-19
2. Tasks
2.1 Create Sprint Back Log
2.2
2
| 2.1 Distribute tasks |  | 2021-09-02 | 2021-09-02 | GP & LL | Action Plan, WBS | Done
4. Final
| 4.1 Prepare Power-Point |  | 2021-09-05 | 2021-09-05 | GP & LL |  | In-progress
| 4.2. Prepare Script |  | 2021-09-05 | 2021-09-05 | GP & LL |  | In-progress
| 4.3 Assign slides |  | 2021-09-05 | 2021-09-05 | GP & LL |  | In-progress
| 4.4 Present |  | 2021-09-30 | 2021-09-30 | GP & LL | Presentation | In-progress
Note on I26: ====== ID#AAAAOotlcBU Lucas Lobo (2021-09-02 10:04:13) Action plan - https://docs.google.com/document/d/1NZkZHo4gkkLN_atZn1ZLj3MDYe3qtMyK/edit?usp=sharing&ouid=103687206531405855352&rtpof=true&sd=true WBS - Proprio ficheiro

## burnout_chart
Day | Target Hours Left | Real Hours Left | João Palma | João Reis | João Santos | Lucas Lobo | Pedro Gouveia
2021-11-12 | 95 | 95 | 0 | 0 | 0 | 0 | 0
2021-11-13 | 90 | 85 | 2 | 2 | 2 | 2 | 2
2021-11-14 | 85 | 85 | 0 | 0 | 0 | 0 | 0
2021-11-15 | 80 | 85 | 0 | 0 | 0 | 0 | 0
2021-11-16 | 75 | 85 | 0 | 0 | 0 | 0 | 0
2021-11-17 | 70 | 85 | 0 | 0 | 0 | 0 | 0
2021-11-18 | 65 | 85 | 0 | 0 | 0 | 0 | 0
2021-11-19 | 60 | 81 |  | 2 |  | 2
2021-11-20 | 55 | 81
2021-11-21 | 50 | 81
2021-11-22 | 45 | 81
2021-11-23 | 40 | 81
2021-11-24 | 35 | 81
2021-11-25 | 30 | 81
2021-11-26 | 25 | 81
2021-11-27 | 20 | 81
2021-11-28 | 15 | 81
2021-11-29 | 10 | 81
2021-11-30 | 0 | 81